## Scope
Sr.no | Features to be deployed
1 | Priority order Phase-1
2 | JobCluster and Priority order extended
3 | Load status change
4 | Zema pipeline extension
5 | Alert log change
Include batch count and partition by
NIDI pipeline enhancement not in PROD
Take unharm notebook backup before notebook deployment

## Run Book
Sr. No | Category | Task | Task Details | Date | Start Time | End Time | Executed By | Status
Ingestion ADF 792 and 876 for batch count
Transformation ADF 287 and 293 for batch count
1 | GitHub | Ingestion cherry-pick for priority order - PR 908
Batch count 10 in ingestion - PR 971
Partition by in transformation - PR 286
2 | GitHub | Transformation cherry-picks for priority order - PR 294 and 302
3 | GitHub | Cherry picks for Job cluster and Priority order changes - PR 305, 315, 316, 322 and 324. Changes only in CP_Data_transformation repo and transformation ADF
4 | GitHub | Cherry-pick PoolCluster commit in ingestion ADF
5 | GitHub | Ingestion cherry picks for load_status log fix - PR - 936, 937, 950, 953
6 | GitHub | Transformation cherry picks for load_status log fix - PR - 306, 307, 309
7 | GitHub | Cherry picks for ZEMA remediation in ingetsion - PR - 943, 954, 957
8 | GitHub | Cherry pick for log Alert fix in transformation - PR 308 Ingestion - 952
cherry pick commit "checking length before splitting" for partition by in ADB
9 | GitHub | Cherry pick PR-91 in CDS_ADB
10 | GitHub | Cherry pick 914 to extend load metadata pipeline worksheet parameter to include cluster_config_id
11 | GitHub | Review
1 | FMS | Add "cluster_config_id" column to config_dataset
2 | FMS | Change transformation ADF wrapper pipeline name in config sheet to "PL_LandingToUnharm_Parameterized_Wrapper.json" and run wrapper load metadata pipeline for any source to reflect the change in config database table
3 | FMS | Change "config_src_load_sequence_no" to 1 for all datasets in metadata sheet and execute below query in db update [cp_data].[config_dataset] set config_value = '1' where config_name = 'config_src_load_sequence_no'
4 | Deployment | Stop all active triggers
5 | Deployment in ingestion ADF | Following to be mentioned in ADFdeploy_param json file and deployed in ingestion ADF: Deploy LS - {"name" : "LS_Databricks_PoolCluster_Parameterized.json} Deploy Pipeline - {"name" : "PL_Common_StoredProcedure_Activity.json"}, {"name" : "PL_GenericToADLS_Parameterized_CPData.json"}, {"name" : "PL_GenericToADLS_Parameterized_CPData_SrcToLand.json"}, {"name" : "PL_GenericToADLS_Parameterized_CPData_SrcToLand_AWS_S3.json"}, {"name" : "PL_GenericToADLS_Parameterized_CPData_SrcToLand_Avro.json"}, {"name" : "PL_GenericToADLS_Parameterized_CPData_SrcToLand_BigQuery.json"}, {"name" : "PL_GenericToADLS_Parameterized_CPData_SrcToLand_Excel.json"}, {"name" : "PL_GenericToADLS_Parameterized_CPData_SrcToLand_FS.json"}, {"name" : "PL_GenericToADLS_Parameterized_CPData_SrcToLand_OracleSID.json"}, {"name" : "PL_GenericToADLS_Parameterized_CPData_SrcToLand_OracleSN.json"}, {"name" : "PL_GenericToADLS_Parameterized_CPData_SrcToLand_REST_API.json"}, {"name" : "PL_GenericToADLS_Parameterized_CPData_SrcToLand_REST_API_Auth2.json"}, {"name" : "PL_GenericToADLS_Parameterized_CPData_SrcToLand_Restful_API.json"}, {"name" : "PL_GenericToADLS_Parameterized_CPData_SrcToLand_SAP_BW.json"}, {"name" : "PL_GenericToADLS_Parameterized_CPData_SrcToLand_SAP_HANA.json"}, {"name" : "PL_GenericToADLS_Parameterized_CPData_SrcToLand_SFTP_NIDI_child.json"}, {"name" : "PL_GenericToADLS_Parameterized_CPData_SrcToLand_SFTP_parent.json"}, {"name" : "PL_GenericToADLS_Parameterized_CPData_SrcToLand_SqlDB_Cloud.json"}, {"name" : "PL_GenericToADLS_Parameterized_CPData_SrcToLand_SqlDB_OnPrem.json"}, {"name" : "PL_GenericToADLS_Parameterized_CPData_SrcToLand_SqlDB_V1_Cloud.json"}, {"name" : "PL_GenericToADLS_Parameterized_CPData_SrcToLand_Sybase_OnPrem.json"}, {"name" : "PL_GenericToADLS_Parameterized_CPData_SrcToLand_TESLA_API.json"}, {"name" : "PL_LoadConfigDatasetColumnData.json"}, {"name" : "PL_LoadMetadata.json"}, {"name" : "PL_GenericToADLS_Parameterized_Wrapper.json"}
6 | Deployment in Transformation ADF | Following to be mentioned in ADFdeploy_param json file and deployed in transformation ADF: Deploy LS - {"name" : "LS_Databricks_JobCluster_Parameterized.json}, {"name" : "LS_Databricks_PoolCluster_Parameterized.json} Delete Pipeline - {"name" : "PL_LandingToDelta_Parameterized_CPData.json"}, {"name" : "PL_LandingToDelta_Parameterized_Wrapper.json"} Deploy Pipeline - {"name" : "PL_LandingToRaw_Parameterized_CPData.json"}, {"name" : "PL_RawToUnharm_Parameterized_CPData.json"}, {"name" : "PL_LandingToUnharm_Parameterized_CPData.json"}, {"name" : "PL_LandingToUnharm_Parameterized_Wrapper.json"}
7 | Deploy sql Stored Procedures | [cp_data].[usp_load_metadata_info] [cp_data].[usp_load_seq_no] [cp_data].[insert_load_status] [cp_data].[update_load_status] [cp_data].[SP_ADF_LOG_ALERTS_COLUMNS_TRANS] | Take back up of SP's before deploying new version
8 | Create config_cluster table | Execute below DDL - SET ANSI_NULLS ON GO SET QUOTED_IDENTIFIER ON GO CREATE TABLE [cp_data].[config_cluster]( [cluster_config_id] [int] IDENTITY(1,1) NOT NULL, [driver_node_type] [nvarchar](100) NULL, [worker_node_type] [nvarchar](100) NULL, [worker_autoscale] [nvarchar](10) NULL, [spark_version] [nvarchar](50) NULL, [cluster_type] [nvarchar](50) NULL, [pool_id] [nvarchar](100) NULL, [cluster_description] [nvarchar](200) NULL, [created_datetime] [datetime] NULL, [created_by] [nvarchar](100) NULL, [modified_datetime] [datetime] NULL, [modified_by] [nvarchar](100) NULL ) ON [PRIMARY] GO ALTER TABLE [cp_data].[config_cluster] ADD CONSTRAINT [PK_cp_data.config_cluster] PRIMARY KEY CLUSTERED ( [cluster_config_id] ASC )WITH (STATISTICS_NORECOMPUTE = OFF, IGNORE_DUP_KEY = OFF, ONLINE = OFF, OPTIMIZE_FOR_SEQUENTIAL_KEY = OFF) ON [PRIMARY] GO
9 | Global Parameters - Transformation ADF | ADLS_ContainerName - String - shell31eunadls2nbnbsmmjd KVScopeName - String - CPDataDatabricksScopeProd ADLS_KVSecretName - String - shell-32-spn-tkreerwcqapckxlqnwoz ADLS_SPN_ClientID - String - 292e976f-649a-4335-96a2-1bf03d0c2012 SQLUserName_ADB - String - CPData_Prod_ADB
10 | Deployment | Logic App deployment | Deploy source variant parameter in the stored proc activity of LogicApp
11 | Deployment | Verify all deployed changes in live mode
12 | Deployment | Restart stopped Triggers

## Active Triggers
{"name" : " | acaciasoft_trigger_for_crss_prelim | .json"}, | {"name" : "acaciasoft_trigger_for_crss_prelim.json"},
{"name" : " | acaciasoft_triggers_for_crss_final | .json"}, | {"name" : "acaciasoft_triggers_for_crss_final.json"},
{"name" : " | Acaciasoft_1_Datasets | .json"}, | {"name" : "Acaciasoft_1_Datasets.json"},
{"name" : " | Acaciasoft_Datasets | .json"}, | {"name" : "Acaciasoft_Datasets.json"},
{"name" : " | Acaciasoft_Datasets_Monthly | .json"}, | {"name" : "Acaciasoft_Datasets_Monthly.json"},
{"name" : " | Acaciasoft_Trigger_for_crss_daily_10 | .json"}, | {"name" : "Acaciasoft_Trigger_for_crss_daily_10.json"},
{"name" : " | Acaciasoft_triggers_For_crss_daily_05 | .json"}, | {"name" : "Acaciasoft_triggers_For_crss_daily_05.json"},
{"name" : " | Acaciasoft_triggers_For_rates | .json"}, | {"name" : "Acaciasoft_triggers_For_rates.json"},
{"name" : " | Aligne_Cloud | .json"}, | {"name" : "Aligne_Cloud.json"},
{"name" : " | Aligne_Datasets | .json"}, | {"name" : "Aligne_Datasets.json"},
{"name" : " | Aligne_Datasets_Delta | .json"}, | {"name" : "Aligne_Datasets_Delta.json"},
{"name" : " | Aligne_Norske_Datasets | .json"}, | {"name" : "Aligne_Norske_Datasets.json"},
{"name" : " | Capex_Datasets | .json"}, | {"name" : "Capex_Datasets.json"},
{"name" : " | CRD_Datasets | .json"}, | {"name" : "CRD_Datasets.json"},
{"name" : " | Crossfutures_Datasets | .json"}, | {"name" : "Crossfutures_Datasets.json"},
{"name" : " | EARL_Datasets | .json"}, | {"name" : "EARL_Datasets.json"},
{"name" : " | edw_cargo_schedules_trigger | .json"}, | {"name" : "edw_cargo_schedules_trigger.json"},
{"name" : " | EDW_Datasets | .json"}, | {"name" : "EDW_Datasets.json"},
{"name" : " | EDW_Offline_Datasets | .json"}, | {"name" : "EDW_Offline_Datasets.json"},
{"name" : " | EMARKET_Datasets | .json"}, | {"name" : "EMARKET_Datasets.json"},
{"name" : " | endur_stusco_Datasets | .json"}, | {"name" : "endur_stusco_Datasets.json"},
{"name" : " | ENERGYCOMPONENT_DATASET | .json"}, | {"name" : "ENERGYCOMPONENT_DATASET.json"},
{"name" : " | EnergyCredit_Datasets | .json"}, | {"name" : "EnergyCredit_Datasets.json"},
{"name" : " | EPEX_Datsets | .json"}, | {"name" : "EPEX_Datsets.json"},
{"name" : " | GMAS_Datasets | .json"}, | {"name" : "GMAS_Datasets.json"},
{"name" : " | GPNA_Datasets | .json"}, | {"name" : "GPNA_Datasets.json"},
{"name" : " | GTMI_Datasets | .json"}, | {"name" : "GTMI_Datasets.json"},
{"name" : " | Kepler_Datasets | .json"}, | {"name" : "Kepler_Datasets.json"},
{"name" : " | KSTAT_Datasets | .json"}, | {"name" : "KSTAT_Datasets.json"},
{"name" : " | NEXTK_Datasets | .json"}, | {"name" : "NEXTK_Datasets.json"},
{"name" : " | NIDI_Dataset | .json"}, | {"name" : "NIDI_Dataset.json"},
{"name" : " | Nucleus_Datasets | .json"}, | {"name" : "Nucleus_Datasets.json"},
{"name" : " | QuantPortal_Datasets | .json"}, | {"name" : "QuantPortal_Datasets.json"},
{"name" : " | RADAR_Datasets | .json"}, | {"name" : "RADAR_Datasets.json"},
{"name" : " | RBP_Datasets | .json"}, | {"name" : "RBP_Datasets.json"},
{"name" : " | RDM_AWS_S3 | .json"}, | {"name" : "RDM_AWS_S3.json"},
{"name" : " | RTDP_BW_Datasets_Daily | .json"}, | {"name" : "RTDP_BW_Datasets_Daily.json"},
{"name" : " | RTDP_BW_Datasets_Monthly | .json"}, | {"name" : "RTDP_BW_Datasets_Monthly.json"},
{"name" : " | RTDP_Curated_Datasets | .json"}, | {"name" : "RTDP_Curated_Datasets.json"},
{"name" : " | SAPHANA_CPDATA_Datasets | .json"}, | {"name" : "SAPHANA_CPDATA_Datasets.json"},
{"name" : " | SAPHANA_DOPS_Datasets_Daily_Once | .json"}, | {"name" : "SAPHANA_DOPS_Datasets_Daily_Once.json"},
{"name" : " | SAPHANA_DOPS_Datasets_Daily_Twice | .json"}, | {"name" : "SAPHANA_DOPS_Datasets_Daily_Twice.json"},
{"name" : " | SAPHANA_DOPS_Datasets_Monthly | .json"}, | {"name" : "SAPHANA_DOPS_Datasets_Monthly.json"},
{"name" : " | SAPHANA_EARL_GSAP_Datasets | .json"}, | {"name" : "SAPHANA_EARL_GSAP_Datasets.json"},
{"name" : " | SAPHANA_Erate_GSAP_Datasets | .json"}, | {"name" : "SAPHANA_Erate_GSAP_Datasets.json"},
{"name" : " | SAPHANA_Erate_STNSAP_Datasets | .json"}, | {"name" : "SAPHANA_Erate_STNSAP_Datasets.json"},
{"name" : " | SAPHANA_Erate_TSAP_Datasets | .json"}, | {"name" : "SAPHANA_Erate_TSAP_Datasets.json"},
{"name" : " | slmt_party_trigger | .json"}, | {"name" : "slmt_party_trigger.json"},
{"name" : " | SLMT_Datasets | .json"}, | {"name" : "SLMT_Datasets.json"},
{"name" : " | Synthesis_Datasets | .json"}, | {"name" : "Synthesis_Datasets.json"},
{"name" : " | TCP_Datasets | .json"}, | {"name" : "TCP_Datasets.json"},
{"name" : " | Terminal_Cockpit_1_Datasets | .json"}, | {"name" : "Terminal_Cockpit_1_Datasets.json"},
{"name" : " | Terminal_Cockpit_2_Datasets | .json"}, | {"name" : "Terminal_Cockpit_2_Datasets.json"},
{"name" : " | Terminal_Cockpit_Datasets | .json"}, | {"name" : "Terminal_Cockpit_Datasets.json"},
{"name" : " | Tesla_Dataset | .json"}, | {"name" : "Tesla_Dataset.json"},
{"name" : " | TRAYPORT_Datasets | .json"}, | {"name" : "TRAYPORT_Datasets.json"},
{"name" : " | TRAYPORT_PREPROCESSOR_TRIGGER | .json"}, | {"name" : "TRAYPORT_PREPROCESSOR_TRIGGER.json"},
{"name" : " | TRIGGER_EPEX_PREPROCESSOR | .json"}, | {"name" : "TRIGGER_EPEX_PREPROCESSOR.json"},
{"name" : " | TRIGGER_NEXTK_PREPROCESSOR | .json"}, | {"name" : "TRIGGER_NEXTK_PREPROCESSOR.json"},
{"name" : " | TRIGGER_TCP_PREPROCESSOR | .json"}, | {"name" : "TRIGGER_TCP_PREPROCESSOR.json"},
{"name" : " | VMIFE_Datasets | .json"}, | {"name" : "VMIFE_Datasets.json"},
{"name" : " | VMIFE_Enhancement_Datasets | .json"}, | {"name" : "VMIFE_Enhancement_Datasets.json"},
{"name" : " | Zema_InterestRate_EONIA_ON_EUR | .json"}, | {"name" : "Zema_InterestRate_EONIA_ON_EUR.json"},
{"name" : " | Zema_InterestRate_ESTR_ON_EUR | .json"}, | {"name" : "Zema_InterestRate_ESTR_ON_EUR.json"},
{"name" : " | Zema_InterestRate_Fallback_EUROBOR_1M_EUR | .json"}, | {"name" : "Zema_InterestRate_Fallback_EUROBOR_1M_EUR.json"},
{"name" : " | Zema_InterestRate_Fallback_LIBOR_1M_EUR | .json"}, | {"name" : "Zema_InterestRate_Fallback_LIBOR_1M_EUR.json"},
{"name" : " | Zema_InterestRate_Fallback_LIBOR_1M_GBP | .json"}, | {"name" : "Zema_InterestRate_Fallback_LIBOR_1M_GBP.json"},
{"name" : " | Zema_InterestRate_Fallback_LIBOR_1M_USD | .json"}, | {"name" : "Zema_InterestRate_Fallback_LIBOR_1M_USD.json"},
{"name" : " | Zema_InterestRate_Fallback_LIBOR_ON_EUR | .json"}, | {"name" : "Zema_InterestRate_Fallback_LIBOR_ON_EUR.json"},
{"name" : " | Zema_InterestRate_Fallback_LIBOR_ON_GBP | .json"}, | {"name" : "Zema_InterestRate_Fallback_LIBOR_ON_GBP.json"},
{"name" : " | Zema_InterestRate_Fallback_LIBOR_ON_USD | .json"}, | {"name" : "Zema_InterestRate_Fallback_LIBOR_ON_USD.json"},
{"name" : " | Zema_InterestRate_Fed_Funds_ON_USD | .json"}, | {"name" : "Zema_InterestRate_Fed_Funds_ON_USD.json"},
{"name" : " | Zema_InterestRate_Natwest_LIBOR_1M_USD | .json"}, | {"name" : "Zema_InterestRate_Natwest_LIBOR_1M_USD.json"},
{"name" : " | Zema_InterestRate_Prime_ON_USD | .json"}, | {"name" : "Zema_InterestRate_Prime_ON_USD.json"},
{"name" : " | Zema_InterestRate_SOFR_ON_USD | .json"}, | {"name" : "Zema_InterestRate_SOFR_ON_USD.json"},
{"name" : " | Zema_InterestRate_SONIA_ON_GBP | .json"}, | {"name" : "Zema_InterestRate_SONIA_ON_GBP.json"},
{"name" : " | ZEMA_Datasets | .json"}, | {"name" : "ZEMA_Datasets.json"},
{"name" : " |  | .json"}, | {"name" : ".json"},
{"name" : " |  | .json"}, | {"name" : ".json"},
{"name" : " |  | .json"}, | {"name" : ".json"},
{"name" : " |  | .json"}, | {"name" : ".json"},
{"name" : " |  | .json"}, | {"name" : ".json"},
{"name" : " |  | .json"} | {"name" : ".json"}

## Roll Back
Sr. No | Task | Task Details
1 | Ingestion cherry-pick for priority order - PR 908 | Revert Commit
2 | Transformation cherry-picks for priority order - PR 294 and 302 | Revert Commit
3 | Cherry picks for Job cluster and Priority order changes - PR 305, 315, 316, 322 and 324. Changes only in CP_Data_transformation repo and transformation ADF | Revert Commit
4 | Cherry-pick PoolCluster commit in ingestion ADF | Revert Commit
5 | Ingestion cherry picks for load_status log fix - PR - 936, 937, 950, 953 | Revert Commit
6 | Transformation cherry picks for load_status log fix - PR - 306, 307, 309 | Revert Commit
7 | Cherry picks for ZEMA remediation in ingetsion - PR - 943, 954, 957 | Revert Commit
8 | Cherry pick for log Alert fix in transformation - PR 308 | Revert Commit
9 | Cherry pick PR-91 in CDS_ADB | Revert Commit
10 | Cherry pick 914 to extend load metadata pipeline worksheet parameter to include cluster_config_id | Revert Commit
11 | Following to be mentioned in ADFdeploy_param json file and deployed in ingestion ADF: Deploy LS - {"name" : "LS_Databricks_PoolCluster_Parameterized.json} Deploy Pipeline - {"name" : "PL_Common_StoredProcedure_Activity.json"}, {"name" : "PL_GenericToADLS_Parameterized_CPData.json"}, {"name" : "PL_GenericToADLS_Parameterized_CPData_SrcToLand.json"}, {"name" : "PL_GenericToADLS_Parameterized_CPData_SrcToLand_AWS_S3.json"}, {"name" : "PL_GenericToADLS_Parameterized_CPData_SrcToLand_Avro.json"}, {"name" : "PL_GenericToADLS_Parameterized_CPData_SrcToLand_BigQuery.json"}, {"name" : "PL_GenericToADLS_Parameterized_CPData_SrcToLand_Excel.json"}, {"name" : "PL_GenericToADLS_Parameterized_CPData_SrcToLand_FS.json"}, {"name" : "PL_GenericToADLS_Parameterized_CPData_SrcToLand_OracleSID.json"}, {"name" : "PL_GenericToADLS_Parameterized_CPData_SrcToLand_OracleSN.json"}, {"name" : "PL_GenericToADLS_Parameterized_CPData_SrcToLand_REST_API.json"}, {"name" : "PL_GenericToADLS_Parameterized_CPData_SrcToLand_REST_API_Auth2.json"}, {"name" : "PL_GenericToADLS_Parameterized_CPData_SrcToLand_Restful_API.json"}, {"name" : "PL_GenericToADLS_Parameterized_CPData_SrcToLand_SAP_BW.json"}, {"name" : "PL_GenericToADLS_Parameterized_CPData_SrcToLand_SAP_HANA.json"}, {"name" : "PL_GenericToADLS_Parameterized_CPData_SrcToLand_SFTP_NIDI_child.json"}, {"name" : "PL_GenericToADLS_Parameterized_CPData_SrcToLand_SFTP_parent.json"}, {"name" : "PL_GenericToADLS_Parameterized_CPData_SrcToLand_SqlDB_Cloud.json"}, {"name" : "PL_GenericToADLS_Parameterized_CPData_SrcToLand_SqlDB_OnPrem.json"}, {"name" : "PL_GenericToADLS_Parameterized_CPData_SrcToLand_SqlDB_V1_Cloud.json"}, {"name" : "PL_GenericToADLS_Parameterized_CPData_SrcToLand_Sybase_OnPrem.json"}, {"name" : "PL_GenericToADLS_Parameterized_CPData_SrcToLand_TESLA_API.json"}, {"name" : "PL_LoadConfigDatasetColumnData.json"}, {"name" : "PL_LoadMetadata.json"}, {"name" : "PL_GenericToADLS_Parameterized_Wrapper.json"} | Deployment in ingestion ADF
12 | Following to be mentioned in ADFdeploy_param json file and deployed in transformation ADF: Deploy LS - {"name" : "LS_Databricks_JobCluster_Parameterized.json}, {"name" : "LS_Databricks_PoolCluster_Parameterized.json} Delete Pipeline - {"name" : "PL_LandingToDelta_Parameterized_CPData.json"}, {"name" : "PL_LandingToDelta_Parameterized_Wrapper.json"} Deploy Pipeline - {"name" : "PL_LandingToRaw_Parameterized_CPData.json"}, {"name" : "PL_RawToUnharm_Parameterized_CPData.json"}, {"name" : "PL_LandingToUnharm_Parameterized_CPData.json"}, {"name" : "PL_LandingToUnharm_Parameterized_Wrapper.json"} | Deployment in Transformation ADF
13 | [cp_data].[usp_load_metadata_info] [cp_data].[usp_load_seq_no] [cp_data].[insert_load_status] [cp_data].[update_load_status] [cp_data].[SP_ADF_LOG_ALERTS_COLUMNS_TRANS] | Deploy previous version of sql Stored Procedures