## Run Book
Sr. No | Task | Task Details | Date | Start Time | End Time | Executed By | Status
1 | Take Backup of files | Copy entire ADLS directories and rename _backup in case of roll-back
1 | Test connection details | Use the connection detials in step 4 and test using native oracle client
2 | Stop Triggers | Ensure triggers are stopped
3 | Update KV Password | Obtain new password from Tom and update in the KV
4 | Enter UAT Conenction Details in the Framework Metadata Sheet | Fill Framework Metadata sheet with new conneciton string and run load_metadata pipeline. HOST = amsdc1-u-s00209.europe.shell.com PORT = 1648 SERVICE_NAME = TESLD07T USER = DTPLATFM
5 | Validate metadata has been updated successfully | Validate the new connection details have been correctly loaded in to the SQL DB
6 | Clear Down every incremental dataset where the schema is changing. Those datsets are: | AB_TRAN - Folders w00443/p00799/p00807 INS_PARAMETER - Folders w00443/p00799/p00807 GAS_PHYS_PARAM - Folders w00443/p00799/p00807 PARAM_RESET_HEADER - Folders w00443/p00799/p00807 COMM_SCHEDULE_HEADER - Folders w00371/p00644/p00632 PWR_PHYS_PARAM Folders - w00443/p00799/p00807 TRAN_SCHEDULE_DETAILS Folders - w00443/p00799/p00807
7 | Clear down the watermarks for the 7 datasets defined above | Reset the watermarks for: AB_TRAN INS_PARAMETER GAS_PHYS_PARAM PARAM_RESET_HEADER COMM_SCHEDULE_HEADER PWR_PHYS_PARAM TRAN_SCHEDULE_DETAILS
8 | Run SLMT pipelines in Debug mode | Do a pipeline run in debug mode for SLMT datsets only and monitor
9 | Announce successful run to team | Put a comms in the CDS chat that the update has been successful - BA to send update comms
10 | Re-enable triggers | Turn on the SLMT triggers once again
11 | Delete back up files | after 1 week of successful ingestion & successful testing, we can delete the backup files

## Roll Back Proceedure
Sr. No | Task | Date | Start Time | End Time | Executed By | Status
1 | Update the Framework Metadata Sheet with the old connection details
2 | Rename current ADLS folder with '_v19' and restore back-up folder be removing '_backup'
3 | Run the load_metadata pipeline for ENDUR SLMT
4 | Validate that the data has loaded in the SQL DB as expected using the query in step 4 above
5 | Run the SLMT pipeline in debug mode
6 | Validate successful loads for all datasets
7 | Re-enable triggers